RESTRICTED / CONFIDENTIAL

DroneArjuna (DA)

AI-Adjusted Project Timeline

Replanned task register assuming Claude-assisted development

ACS Technologies Limited

Document Date: 6 June 2026

Classification: RESTRICTED / CONFIDENTIAL

62 tasks across 6 phases  |  ~9–10 weeks AI-adjusted  |  ~4–5× speedup vs human baseline

# Table of Contents

# 1. Calibration Basis

From session benchmarking, five tasks that would each be a half-day to full-day without AI (ManualControlPanel, CameraWindow, LiveOpsPanel, ConnectModal port scan, PlanWorkspace 3-panel layout) were each completed in 10–20 minutes — roughly a 10–15× speedup on pure code-generation work. The speedup is not uniform across task types.

| Task Type | Human Baseline | With AI | Multiplier |
| --- | --- | --- | --- |
| CRUD endpoints + model + schema | 1–2 days | 1–2 h | 10× |
| DB model + Alembic migration | ½ day | 20 min | 8× |
| Frontend component (forms, lists, panels) | ½–1 day | 15–30 min | 12× |
| pytest suite (unit + integration) | 1–2 days | 1–2 h | 8× |
| Complex algorithm (geofencing, deconfliction) | 3–5 days | 1–2 days | 3× |
| Third-party library integration (Cesium, Celery) | 1–2 weeks | 3–5 days | 3× |
| ML pipeline (YOLOv8, workers) | 2–3 weeks | 5–7 days | 3× |
| Infrastructure (Docker, CI, nginx) | 3–5 days | 1–2 days | 3× |
| SITL environment + hardware validation | 1–2 weeks | 1–2 weeks | 1× (fixed) |
| Architecture decisions + review | — | — | 1× (fixed) |

# 2. Revised Effort Scale

All task estimates in this document use the following AI-adjusted effort symbols:

| Symbol | With AI | Human Baseline |
| --- | --- | --- |
| XS | 15–30 min | ½ day |
| S | 1–2 h | 1 day |
| M | 3–6 h | 2–3 days |
| L | 1–2 days | 4–7 days |
| XL | 3–5 days | 1–2 weeks |
| ⏳ (fixed) | Human-gated | No change |

# 3. Phase 1 — Exit Gate

Phase total: 3–4 calendar days  (human baseline: ~2 weeks)

Note: SITL environment provisioning (P1-03) is the bottleneck, not code.

| # | Task | AI Effort | Note |
| --- | --- | --- | --- |
| P1-01 | GET /api/drone-control/ports — enumerate serial + UDP/TCP SITL ports | S (1h) | Straightforward |
| P1-02 | POST /api/drone-control/autoconnect — probe ports, first success | S (1h) | Depends P1-01 |
| P1-03 | ArduPilot SITL smoke test — bring up simulator, verify full stack | ⏳ (2–3 days) | Env setup, not code |
| P1-04 | pytest auth suite — login, refresh, expiry, RBAC per role | S (1.5h) | — |
| P1-05 | pytest drone-control suite — connect, command, WS frame | S (1.5h) | Needs P1-03 |
| P1-06 | Tag v1.0.0, baseline DA-STD/STR docs | XS (20 min) | Admin |

# 4. Phase 2 — Drone Master + Mission Planner

Phase total: 5 calendar days  (human baseline: 6–8 weeks)

## 4A. Payload Type CRUD

### Subtotal: ~6 hours

| # | Task | AI Effort |
| --- | --- | --- |
| P2-01 | Payload/PayloadType models + migration 003 | XS (20 min) |
| P2-02 | POST/GET/PUT/DELETE /api/master/payload-types | S (1h) |
| P2-03 | POST/GET/PUT/DELETE /api/master/payloads (instances) | S (1h) |
| P2-04 | Replace inventory stub GET /api/inventory/payloads | XS (30 min) |
| P2-05 | Weight compliance check in MissionValidator | XS (30 min) |
| P2-06 | PayloadManager.tsx — full CRUD UI | S (1.5h) |
| P2-07 | Payload assignment in DroneInstanceManager.tsx | XS (30 min) |

## 4B. Configuration Templates

### Subtotal: ~2 hours

| # | Task | AI Effort |
| --- | --- | --- |
| P2-08 | DroneConfigTemplate model + migration 004 | XS (20 min) |
| P2-09 | GET/POST/PUT/DELETE /api/master/config-templates | S (1h) |
| P2-10 | Config template picker in ConnectModal.tsx | XS (30 min) |

## 4C. Mission Planner Hardening

### Subtotal: ~3 days

| # | Task | AI Effort | Note |
| --- | --- | --- | --- |
| P2-11 | Geofence draw & edit tools in MapCanvas.tsx | L (1.5 days) | Leaflet Draw + custom handles |
| P2-12 | Geofence validation visual feedback on map | S (1h) | — |
| P2-13 | Survey-grid wizard UI | M (4h) | — |
| P2-14 | Waypoint actions UI per waypoint (action + params) | M (3h) | — |
| P2-15 | Mission status workflow buttons | XS (30 min) | Backend endpoint exists |
| P2-16 | Pre-flight simulation preview animate | M (4h) | — |
| P2-17 | pytest flight suite | S (1.5h) | — |

# 5. Phase 3 — Advanced Flight + Visualisation

Phase total: 10–12 calendar days  (human baseline: 8–10 weeks)

Note: Cesium.js is the dominant cost — a 600k-line library with its own paradigm.

| # | Task | AI Effort | Note |
| --- | --- | --- | --- |
| P3-01 | Cesium.js integration — scaffold Map3DCanvas.tsx | XL (3–4 days) | Large novel library; expect iteration |
| P3-02 | 3D terrain draping for mission routes | L (1.5 days) | Depends P3-01 |
| P3-03 | 3D live drone tracking (glTF model + telemetry feed) | M (4h) | Depends P3-01 |
| P3-04 | Telemetry replay player (timeline scrubber) | M (4h) | — |
| P3-05 | Geofence enforcement — breach detection + auto-RTL | L (1.5 days) | Algorithm + RabbitMQ event |
| P3-06 | Multi-drone airspace deconfliction | L (2 days) | Geometry-heavy |
| P3-07 | Vessel-relative home point — live update from feed | M (3h) | — |
| P3-08 | HF position feed end-to-end validation | M (4h) | — |
| P3-09 | pytest advanced flight suite | S (1.5h) | — |

# 6. Phase 4 — Drone Inventory (Knowledge Base)

Phase total: 7–9 calendar days  (human baseline: 6–8 weeks)

Note: Elasticsearch is the dominant cost. P4-01–P4-05 and P4-07 can be completed in a single focused day.

| # | Task | AI Effort | Note |
| --- | --- | --- | --- |
| P4-01 | InventoryWorkspace.tsx — new 6th workspace tab | S (1.5h) | — |
| P4-02 | Drone catalogue browser — card grid + facet filters | M (3h) | — |
| P4-03 | Drone spec detail page + performance chart | M (3h) | — |
| P4-04 | Side-by-side comparison view | S (1.5h) | API already exists |
| P4-05 | Payload catalogue browser | M (2h) | Depends P2-06 |
| P4-06 | Elasticsearch integration (replace ILIKE) | XL (3–4 days) | New infra + index mapping |
| P4-07 | Instant search bar (debounced) | XS (30 min) | — |
| P4-08 | Threat system / ORBAT model + knowledge-base page | L (2 days) | Novel domain model |

# 7. Phase 5 — Drone Analyst (AI/CV Pipeline)

Phase total: 12–14 calendar days  (human baseline: 10–12 weeks)

Note: ML model environment (CUDA/GPU, model weights, Celery worker config) is the irreducible complexity.

| # | Task | AI Effort | Note |
| --- | --- | --- | --- |
| P5-01 | Persist analysis jobs to DB — AnalysisJob model + migration 005 | XS (30 min) | — |
| P5-02 | MinIO upload endpoint (POST /api/analyst/upload) | S (1.5h) | — |
| P5-03 | Celery worker infrastructure — broker config, worker/ directory | L (1.5 days) | New infra; Docker Compose changes |
| P5-04 | YOLOv8 object detection Celery task | L (2 days) | ML model setup + GPU config |
| P5-05 | Change detection worker (pixel-diff algorithm) | L (1.5 days) | Depends P5-03 |
| P5-06 | Video frame extraction Celery task | M (4h) | Depends P5-03 |
| P5-07 | Analyst workspace UI — job submission form | M (3h) | — |
| P5-08 | Detection results viewer — bounding box overlay | L (1.5 days) | Complex canvas rendering |
| P5-09 | Change detection map layer in Plan/Fly workspaces | M (3h) | — |
| P5-10 | Telemetry analytics dashboard — rich charts | M (3h) | API already exists |
| P5-11 | Automated telemetry report PDF export | L (2 days) | — |

# 8. Phase 6 — Hardening, Security + UX Polish

Phase total: 5–6 calendar days  (human baseline: 6–8 weeks)

| # | Task | AI Effort | Note |
| --- | --- | --- | --- |
| P6-01 | Full pytest coverage pass — ≥80% line coverage | L (1.5 days) | — |
| P6-02 | JWT refresh rotation + Redis token blacklist | S (1.5h) | — |
| P6-03 | Rate limiting on auth (slowapi) | XS (30 min) | — |
| P6-04 | Input sanitisation + SQL injection audit | M (3h) | — |
| P6-05 | TLS/HTTPS nginx reverse proxy | S (1.5h) | — |
| P6-06 | WCAG 2.1 AA pass — focus rings, aria, contrast | M (4h) | Needs human visual review |
| P6-07 | React error boundaries per workspace | XS (30 min) | — |
| P6-08 | Service worker + offline indicator | M (3h) | — |
| P6-09 | Locust load test — 10 drones × telemetry + 3 missions | M (3h) | — |
| P6-10 | Docker image hardening (non-root, read-only fs) | S (1.5h) | — |
| P6-11 | GitHub Actions CI pipeline | M (3h) | — |

# 9. Revised Summary

| Phase | Tasks | AI-Adjusted | Human Baseline | Speedup |
| --- | --- | --- | --- | --- |
| Phase 1 — Exit Gate | 6 | 3–4 days | ~2 weeks | 3–4× (SITL bottleneck) |
| Phase 2 — Drone Master + Mission | 17 | 5 days | 6–8 weeks | ~10× |
| Phase 3 — Advanced Flight + Viz | 9 | 10–12 days | 8–10 weeks | ~4× (Cesium bottleneck) |
| Phase 4 — Drone Inventory | 8 | 7–9 days | 6–8 weeks | ~6× |
| Phase 5 — Drone Analyst AI | 11 | 12–14 days | 10–12 weeks | ~5× (ML env bottleneck) |
| Phase 6 — Hardening + Polish | 11 | 5–6 days | 6–8 weeks | ~8× |
| TOTAL | 62 | ~9–10 weeks | ~38–48 weeks | ~4–5× |

# 10. Week-by-Week Sprint Plan

Week 1 — Phase 1 Exit Gate

- Mon–Tue: P1-01, P1-02 (ports + autoconnect) + P1-04 (auth tests)

- Wed–Fri: P1-03 SITL environment setup ← provision simulator, unblock P1-05

- Fri: P1-05 (control tests), P1-06 (v1.0.0 tag)

Milestone: Phase 1 closed

Week 2 — Phase 2 Backend

- Mon: P2-01→P2-05 (payload model + all backend CRUD) + P2-08→P2-09 (config template backend) — same sitting

- Tue: P2-06→P2-07 (PayloadManager UI), P2-10 (config picker)

- Wed–Thu: P2-11 (geofence draw tools) ← largest Phase 2 task

- Fri: P2-12, P2-13, P2-14, P2-15 (validation UI, survey wizard, waypoint actions, status buttons)

Milestone: Phase 2 backend + data layer closed

Week 3 — Phase 2 Completion + Phase 4 UI

- Mon: P2-16 (simulation preview), P2-17 (flight tests) → Phase 2 fully closed

- Tue–Fri: P4-01→P4-05, P4-07 (inventory UI — full knowledge base browser, spec pages, compare, search bar)

Milestone: Phase 4 UI closed (Elasticsearch deferred)

Weeks 4–5 — Cesium + Analyst Foundation

- P3-01: Cesium scaffold (4 days — largest remaining task)

- Parallel: P5-01 (persist jobs), P5-02 (MinIO upload), P5-07 (analyst workspace UI), P5-10 (telemetry dashboard)

Weeks 5–6 — Phase 3 Completion

- P3-02, P3-03: 3D terrain draping + live drone tracking

- P3-04: Telemetry replay player

- P3-05, P3-06: Geofence enforcement + multi-drone deconfliction

- P3-07, P3-08: HF position feed + vessel-relative home

- P3-09: Advanced flight test suite

Milestone: Phase 3 closed

Weeks 6–7 — Phase 5 ML Pipeline

- P5-03: Celery worker infrastructure

- P5-04, P5-05: YOLOv8 detection + change detection workers

- P5-06: Video frame extraction

- P5-08, P5-09: Detection results viewer + map layer

- P5-11: PDF report export

Milestone: Phase 5 closed

Weeks 7–8 — Phase 4 Completion

- P4-06: Elasticsearch integration (3–4 days)

- P4-08: Threat system / ORBAT model + knowledge-base page

Milestone: Phase 4 fully closed

Weeks 8–9 — Phase 6 Hardening

- P6-01→P6-11: Full hardening sprint (pytest coverage, JWT hardening, rate limiting, WCAG, CI pipeline)

Milestone: Phase 6 closed

Weeks 9–10 — Buffer + Integration Testing

- Buffer + integration testing + DA-STD / DA-STR baseline update

- Final QA on real SITL with all phases active simultaneously

Milestone: PROJECT COMPLETE

# 11. What AI Does Not Accelerate

The following bottlenecks remain at their original human-baseline duration regardless of AI coding assistance. These are the true constraints on delivery velocity.

| Bottleneck | Why It Is Fixed |
| --- | --- |
| SITL environment | Downloading ArduPilot, configuring Docker networking, forwarding MAVLink ports — environment work, not code |
| GPU/ML environment | YOLOv8 needs CUDA drivers, model weights downloaded, Docker GPU pass-through configured |
| Elasticsearch cluster | Another Docker service, index mapping design, data migration run |
| WCAG visual review | Must be done by a human looking at the rendered UI, not code inspection |
| Security audit | Penetration testing, threat modelling, manual code review beyond linting |
| Architecture decisions | Where to put geofence enforcement boundary, event schema for RabbitMQ — judgement calls |
| Integration debugging | When the SITL drone doesn’t behave as documented, or Celery task silently fails — requires iteration on running systems |

AI compresses the coding phase from months to weeks, but every task with an “environment setup” component or a “test with real hardware” component remains at its original duration. The project is not 10× faster overall — it is closer to 4–5×, with the remaining constraint being infrastructure provisioning, external system integration, and the irreducible complexity of novel third-party libraries such as Cesium.